## Index
GAP Hardware store Project Correspondence Log
Logged by
Sowmya Vasantharao
Srivani Nampally
Swapna Jaidi
Shalini Raigir

## Correspondence Log
GAP Hardware store Project Correspondence Log
Item No. | Date | Correspondence Type | In/Out | From | To | Keyword | Description
1 | 2018-08-20 | Meeting | In | Samantha Goss | Project Team | Requirement Gathering | Requirements provided to project team for GAP Hardware store website development
2 | 2018-08-24 | email | Out | Srivani (On behalf of project team) | Samantha Goss | Requesting for Documents | Requested for content on About us, contact us and Help Pages. Application and Order forms requested.
3 | 2018-08-24 | email | In | Samantha Goss | Project team | Further documents | Confirmed that the content will be provided by later in the day
4 | 2018-08-24 | email | In | Samantha Goss | Project team | Forms Provided | Content for Registration and product order form provided
5 | 2018-08-24 | email | Out | Srivani (On behalf of project team) | Samantha Goss | Confirmation of content | Content for forms received and verified
6 | 2018-08-29 | email | Out | Sowmya (On behalf of project team) | Samantha Goss | Meeting minutes and queries regarding requirements | Meeting minutes from requirements gathering meeting sent to Client and queries in regards to requirements after analysing as a team.
7 | 2018-08-30 | email | In | Samantha Goss | Project team | Content provided along with confirming queries | Content for About us, Help and contact us pages provided along the answering the queries about requirements
8 | 2018-08-30 | email | Out | Sowmya (On behalf of project team) | Samantha Goss | Confirmation of content | Required Content for web pages is received and confirmed